## Implementation list
| Lead CE: partner lead customising expert | CBC: SAP central business configuration
| PLoB CE: partner line of business customising expert | IAS: SAP Cloud Identity Access
| CLoB E: customer line of business expert | IPS: SAP Cloud Identity Provisioning
skip to acronym list
PHASE | ACTIVITY | OWNER | SYSTEM | APP | NOTES
CORPORATE STRATEGY AND INITIATIVE MANAGEMENT (PRE-PROJECT)
| Initiative identified: assign sponsor and initiative leader | Executive board | - | - | Usually from strategic planning or acute issues
| Create initiative team to define vision, high level scope, business case | Initiative lead | - | - | Things can start to go wrong at this early stage if the right expertise isn't present in initial visioning and planning
| Build vision (very high level scope and design) | Initiative team |  |  | Assumption based high level vision of the future process, systems, data, reporting
| Build business case | Initiative team | - | - | Target benefits/rationale, costs, risks, impacts, clear assumptions
| Make decision to pursue SAP S/4HANA Cloud | Executive board | - | - | This leads to engaging with SAP over scope, solution, licenses etc.
| Identify/plan change management approach | Sponsor | - | - | Recommend to utilise Prosci ADKAR
| Identify and launch pre-preparation projects, key examples: |  |  |  | Depending on the current state, pre-projects can significantly enhance the quality of the SAP design and build, whilst also de-risking the programme.
| Target operating model | Sponsor | - | - | If there are significant organisation changes in parallel with SAP it may make sense to produce a target operating model as an initial step. This can help ensure processes and roles in SAP fit with the strategic organisation direction
| Conceptual data model and reporting design | Sponsor | - | - | If legacy systems have reporting issues and/or harminised reporting is a key benefit, it may make sense to run a conceptual re-design of key reporting hierarchies before starting SAP e.g. chart of accounts, profit centers, customer hierarchy, etc.
| Legacy system data cleansing | Sponsor | - | - | If master data and transactional data have not been well managed or cleansed, this can be a significant issue during SAP implementation, this can take a long time to fix.
Resourcing: individuals and delivery partners
| Identify key internal project team roles for next phase | Initiative lead | - | - | Identify candidates and start internal recruiting process Identify backfiling where needed
| Systems integrator partner selection | Sponsor | - | - | If relying on an external partner or SAP for implementation
DISCOVER
| Staff resources for discover phase team | Initiative lead | - | - | For example: - Process/technology owners for scope identification/confirmation - Enterprise architects for IT principles alignment - Procurement for contract and licensing discussions
| Discover phase kick-off | Initiative lead | - | - | Project team + stakeholders Review outcome of previous activities Review detailed plan for phase
| Build on initial business case with specifics for S/4HANA Public Cloud | Initiative lead | - | - | High level scope, benefits, costs, risks etc.
| Complete SAP digital discovery assessment (DDA) | Initiative lead | - | DDA | Detailed questions about business processes Helps to decide between public and private cloud Provides baseline initial scope for refinement during PREPARE/EXPLORE
| Make purchase decision | Executive sponsor | - | -
| Sign S/4HANA Cloud Contract | Executive sponsor | - | - | Signer received PO confirmation e-mail (purchase details and next steps)
| Welcome email on contract start date | IT contact or 'signer' | - | - | Detailed information about starting project
| Welcome email from SAP BTP | IT contact or 'signer' | - | -
| Attend onboarding webinar | Project manager or IT contact | sap.com | - | SAP webinars covering everything about getting started with the project (Navigate to the SAP customer onboarding resource center)
| Start legacy system data preparation as soon as possible |  |  |  | (Ideally already launched as a project)
| Start analysis and cleansing of master data and transactional data | Data lead | - | - | Proceed with EXPLORE activities listed in the next phase ASAP
Project planning
| Create a work breakdown structure including estimation of effort for the work based on the defined scope. As part of this identify the critical path and minimum project duration. | Project manager | - | - | Often SAP program target go-live dates are set without formal scope-based effort estimation. Even if a target go-live date and duration is already set, it's still worth a formal effort and duration estimation to identify feasibility, and look at corrective actions.
| Identify go-live date or validate pre-defined target date | Project manager | - | - | Consider the easiest migration is at fiscal year end. This removes the need to migrate P&L balances, and also will reduce the number of open items.
Project resourcing
| Staffing of internal project team members for next phase | Sponsor | - | - | Including clear role descriptions and responsibilities
| Recruit external contractors/3rd party service providers | Sponsor | - | - | Including clear role descriptions and responsibilities
| Pre-plan/line-up potential need for resources later | Sponsor | - | - | If gaps are expected development resources may be required later. This could include skills such as ABAP, integration, Python, etc. Start to plan for this potential early.
Change & communications management
| Identify all potentially impacted parties | Change manager | - | - | Stakeholders, customers, end users (internal and external)
| Hold initial change management surveys/interviews/discussions | Change manager | - | - | Ideally a review of potential change impacts from across the organisation can be collected prior to prepare to allow time to adjust the scope and preparation approach if needed. At this stage focus on Prosci ADKAR: - A: Awareness of the need for change - D: Desire to participate and support the change
| Internal lessons learned workshop: hold workshop to look at internal history with ERP projects, try to capture past issues and failures and plan to avoid | Project manager | - | - | Build learnings into project approach and change approach
| Request SAP or partner to run lessons learned workshop on other organisations experiences with S/4HANA Cloud Public | Partner PM | - | - | Build learnings into project approach and change approach
Project & stakeholder management
| Document and deploy project management | Project manager | - | - | Scope management, plan management, issues management, risk management, change management, resource management, escalation procedure, reporting procedure, meeting schedules, ways of working.
| Stakeholder identification and analysis | Project manage and change manager | - | -
| Create stakeholder collaboration plan | Project manager and change manager | - | - | Information updates frequency/content, workshops schedule, key reviews (requirements, design, etc.)
| Discover stage gate GO / NO GO | Project manager | - | - | Check: - DDA results indicate S/4HANA Cloud Public is suitable - Project team resources identified and available - 3rd party partner/SAP engaged and available - Stakeholder alignment on benefits, scope, and approach
| Detailed plan for next phase - shared & presentation walkthrough sessions | Project manager | - | - | Team for next phase should be 100% clear on activities, templates, responsibilities etc.
PREPARE
| Phase kick off | Project manager
Set up and onboard project team, key roles include:
Onboarding of 3rd party project team
| Partner project manager and partner stakeholder | Project manager | - | -
| Lead configuation expert (SAP / partner) | Partner PM | - | -
| Partner or SAP line of business experts (1-2 per area) | Partner PM | - | -
| If new to the business, recommend to run various trainings | Project manager | - | - | Business model, IT architecture, processes, controls etc.
| Provisioning of any hardware if required | IT contact | - | - | For example company laptops if needed for network tools
Internal team
| Sponsor(s) and steering committee | Sponsor | - | -
| IT contact | Sponsor | - | -
| Project manager | Sponsor
| Line of business experts | Sponsor/stakeholders | - | - | It is critical that the sponsor and stakeholders identify experts in each line of business that can represent their processes. They should be available for the entire project duration and be qualified to accept standard processes and identify gaps. Number depends on size/complexity of project and LoB SAP recommends 2-3 per LoB.
| Change manager(s) | Sponsor | - | -
| Extended team (as necessary, scope dependant) | Project manager | - | - | Examples: integration, developers, data migration, enterprise architects
| Plan / run internal team project training | Project manager | - | - | SAP training / partner led training Implementation approach, LoB config, etc.
Systems provisioning
| Provision the S/4HANA Cloud Landscape Bundle: | IT contact | SAP for Me | - | Systems for EXPLORE phase. S/4HANA dev/test/prod provisioned later
| 1) Cloud Identity Services |  | - | - | Includes authentication (IAS) and provisioning (IPS) services
| 2) S/4HANA Starter System |  | - | - | Includes development client 80, and customising client 100 With S/4HANA Cloud Public development is split into two clients, the customising client 100 is used for the majority of configuration. Client 80 is reserved for more complex custom developments.
| 3) Cloud Application Lifecycle Management (Cloud ALM) |  | - | - | Used as an implementation management tool
| 4) Central Business Configuration (CBC) |  | - | - | Used as a central reference point for SAP configuration
| IT contact receives emails with login information | IT contact | Email | -
| Activate Cloud Identity Authentication Service (IAS) | IT contact | IAS | - | Must be activated first. Use link in provisioning email
| Clould Application Lifecycle Management (ALM) set up |  |  |  | Cloud ALM will be used for project, requirements & design management
| Create project in Cloud ALM | Partner PM | ALM | - | SAP Activate Roadmap: SAP S/4HANA Cloud Public Edition (3-system landscape) - Implementation
| Review standard roles | Partner PM | ALM | -
| Create/change roles in Cloud ALM | Partner PM | ALM | - | For example: one role for each LoB area
| Add team members to roles in Cloud ALM | Partner PM | ALM | - | Turn of any roles not required
| Add general dates in timeboxes in Cloud ALM | Partner PM | ALM | - | Note: typically fit to standard takes the longest time
| Assign scopes in Cloud ALM | Partner PM | ALM | Manage scopes apps | Initial scope based on DDA, may evolve through fit to standard
| Deploy content in S/4HANA Cloud Starter System (S4 SS) |  |  |  | S/4HANA Cloud Starter System is used to demo standard processes The processes are aligned with SAP Signavio Best Practices
| Add users to Central Business Configuration using IAS |  |  |  | CBC is used to configure S/4HANA Public Cloud
| Create excel and fill in with user details, save as .csv | IT contact | IAS | - | File format: status, loginName, mail, firstName, lastName, groups
| Login to IAS, select 'import users tile', load .csv | IT contact | IAS | Import users tile | Once imported, activation emails are sent to users
| Login to IPS and run job to replicate users and permissions | IT contact | IPS | - | Run this replication immediately as IAS emails were already sent
| Create two spaces in CBC | Lead CE | CBC | - | Use space type 'evaluation' ('enterprise management' brings all LoB) One space for development client 80, one for customising client 100
| In each space confirm scope and configuration |  |  |  | This is for demo content, so it's mostly confirmations
| Scope | Lead CE | CBC | - | Enterprise management scope bundle includes all LoB best practices These provide the ability to demo processes during fit-to-standard
| Countries & ledgers | Lead CE | CBC | - | If multiple countries/regions are in scope choose countries/regions used
| Ledgers | Lead CE | CBC | - | If multiple ledgers are required, choose them. For example: IFRS = 1GA, US GAAP = 2VA
| Finance settings | Lead CE | CBC | - | Confirm FSV: K4 (4 special periods) Confirm group currency (If required further finance customisation will be part of dev build later)
| Organisation structure | Lead CE | CBC | - | Contries/regions above, drive selection of a pre-configured organisation structure for the best practices demo. This is aligned with the Signavio test scripts. (SAP recommends not to adjust at this stage)
| Product specific configurations | Lead CE | CBC | - | Minimal/none at this stage as it's just standard processes in the starter system
| Share settings with team | Lead CE | CBC | - | Lead CE should share the above settings with LoB CEs to assist with their preparation to run demos in fit-to-standard
| Assign deployment target | Lead CE | CBC | - | Connect CBC to S/4HANA Cloud Starter System
| Deploy scope and organisation structure | Lead CE | CBC | - | Deploy from CBC to S/4HANA Cloud Starter System
| Add team members to workspace | Lead CE | CBC | - | Pre-requisite: ensure team members are created in Cloud Identity with permissions for CBC
| Assign CBC roles | IT contact | CBC | - | Lead configruation expert: SAP_CBC_CONSUMPTION_PROGRAM_LEAD LoB CE: SAP_CBC_CONSUMPTION_KEY_USER Project managers: SAP_CBC_CONSUMPTION_AUDITOR IT contact: SAP_CBC_CONSUMPTION_AUDITOR
| Set up project team in S/4HANA Starter System |  |  |  | Starter system approach: use standard roles to demo standard processes
| IT contact logs in to S/4HANA Starter System | IT contact | S4 SS | - | IT contact has SAP_BR_ADMINISTRATOR which gives access to administraiton tab
| Activate all SAP standard roles in S/4HANA Starter System | IT contact | S4 SS | Business Roles Template | Administration > Identity and Access Management > Business Roles Template Select all roles, choose 'create business role' Choose assign spaces based on SAP-delivered space This makes all roles available to be assigned to users.
| IT contact assigns themselves BR_ADMINISTRATOR in S/4HANA starter system | IT contact | S4 SS | - | Edit 'user name = login name for IAS' Remove SAP_BR_ADMINISTRATOR, add BR_ADMINISTRATOR
| Create users for project team in S/4HANA starter system | IT contact | S4 SS | Manage Workforce App | Pre-requisite: users should already be created in IAS Administration > Workforce Master Data > Manage Workforce > Import > Worker Download template, complete with user details, and then upload
| Assign BR_ADMINISTRATOR to all project team members in S/4HANA starter system | IT contact | S4 SS | Maintain Business Roles | This allows all team members to manage permissions to create test users for fit-to-standard sessions
| Verify users have assigned launchpad in S/4HANA starter system | IT contact | S4 SS | - | Administrator > assigned launchpad spaces No apps will display if no space is assigned
| Download users with their assigned permissions from the S/4HANA starter system and upload to IAS to validate and send activation emails | IT contact | S4 SS | Maintain Business Users Identity Provider App | Download from starter systems and upload to IAS. This will validate users, and generate activation emails
Change and communications management
| Formal communication of project team to stakeholders and wider audience including clear list of contacts | Change manager | - | - | This is important to avoid innacurate rumours spreading related to the project and also to ensure people can get to the right point of contact with questions at any point
| Launch project information sharing space | Change manager | - | - | Recommend to have an online reference with basic project information, Q&A etc.
| Continue discussions, workshops and communications to identify change impacts. |  |  |  | At this stage continue with focus on Prosci ADKAR: - A: Awareness of the need for change - D: Desire to participate and support the change
Project and stakeholders management
| There should be a formal workshop with line of business leaders (stakeholders) on the role of the line of business expert. The stakeholders should agree that the nominated business experts has authority to represent requirements and agree to solutions for their line of business. | PM / CM | - | - | Often on SAP programs late requirements appear during acceptance testing due to a lack of formality around the knowledge and commitment needed during requirements gathering.
| Prepare phase Go / No Go | Project manager | - | - | Check: - Project team fully resourced - Project team training/knowledge building complete - Systems, tools, and materials for explore ready - Appropriately qualified and experienced Line of business experts
| Project manager publishes detailed plan for Explore (Assess) | Project manager | - | - | Circulate plan Workshop\presentation to team to explain and discuss
EXPLORE (ASSESS)
| Phase kick off | Project manager
| Review DDA in preparaton for x-LoB 'fit-to-standard' | Partner lead CE | - | - | x-LoB means any topic that doesn't fit into a single line of business May include topics like organisation structure
| Review DDA - business proceses, known integrations | Partner LoB CE | - | -
| Co-ordinate Business Driven Configuration Questionnaire (BDCQ) |  | - | - | This is a questionnairre to gather information for S/4HANA configuration
| Send to x-LoB business experts | Project management | - | - | Business experts may need to co-ordinate with others to complete
| Send to LoB business experts | Project management | - | - | Business experts may need to co-ordinate with others to complete
| Schedule meetings to review BDCQ | LoB CE | - | -
| Loop back and check BDCQ impacts on DDA | LoB CE, lead CE, project managers | - | - | The DDA is the master reference for scope and document the sponsor and stakeholder are familiar with, it should be udpated with any changes.
Prepare for fit-to-standard workshops
| Review in scope proceses & group into workshops | LoB CE | - | - | Test scripts size can help estimate required workshop lengths Group processss by role into workshops with same LoB experts
| Schedule workshops & invite LoB experts | LoB CE | - | -
| Invite change manager and specialists as needed | LoB CE | - | - | Some LoB workshops may require data experts, developers, etc.
| Prepare 'mini-kick off' presentation | LoB CE | - | -
| Prepare 'fit-to-standard' presentation | LoB CE | - | -
| Download test scrips from SAP Signavio Process Manager | LoB CE | Signavio | -
| Create test users for each role in scripts | LoB CE | S4 SS | -
| Do test run of scripts and time how long it takes | LoB CE | S4 SS | -
| Plan which analytical apps to demo per LoB | LoB CE | - | -
| Prepare other accelerator and documents | Lead CE / LoB CE | - | - | Sharing links to online training videos may help business experts prepare.
| Prepare starter system for fit-to-standard workshops | LoB CE
| Create test users | LoB CE | S4 SS | Manage Workforce App | The system is already provisioned, but each test user should be set up with a role: 'employee' plus one primary business role. Name the users in a way LoB business experts will recognise
| Run business process fit-to-standard workshops: |  |  |  | Recommend 2 LoB CE and at least 2 LoB Experts per business role
| Organisation structure workshop | Lead CE | S4 SS | - | Suggested by SAP as a specific workshop
| Chart of accounts workshop | Lead CE | S4 SS | - | Suggested by SAP as a specific workshop
| Run all other LoB workshops | LoB CE | S4 SS | - | As pre grouping designed in workshop preparation
| For above workshops, suggest to cover: |  |  |  | Workshops need to cover many topics
| Present mini-kick off | Lead CE / LoB CE | - | - | Key principles, design and build approach, ownership, etc.
| Demo SAP Signavio | Lead CE / LoB CE | Signavio | - | Process flows, test scripts, tutorials
| Demo business process in S/4HANA Starter System | Lead CE / LoB CE | S4 SS | -
| Demo embedded analytics apps | Lead CE / LoB CE | S4 SS | - | See dedicated section below with more details on embedded analytics
| Demo various ways to access help in Fiori | Lead CE / LoB CE | S4 SS | -
| Demo Joule | Lead CE / LoB CE | S4 SS | -
| Discuss process fit and identify gaps | Lead CE / LoB CE | - | -
| Review standard business roles and capture role gaps | Lead CE / LoB CE | - | - | Accelerator: 'Application - Workplace List'
| Review Fiori space/page/app layout and capture desired changes |  |  |  | Closely related to role discussion
| Review list of objects for migration | Lead CE / LoB CE | - | - | Where an object represents a set of data made up of fields Including master data and transactional data Examples: material records, accounts, balances, open items
| Review known integration requirements from DDA and adjust | Lead CE / LoB CE | - | - | Review systems sending or receiving data to S/4HANA It's likely DDA participants wouldn't know all details of all integration
| Gather remaining BDCQ configuration values | Lead CE / LoB CE | BDCQ | - | Validate L2 answers, capture L3
| Update requiremens in Cloud ALM during workshop | Lead CE / LoB CE | ALM | - | Recommended to have one project team member update Cloud ALM directly during the 'fit-to-standard' workshop to ensure the discussion is captured correctly
| Identify change impacts | Change manager |  |  | Ideally a change manager participates in the 'fit-to-standard' and notes potential change impacts based on the LoB CE / LoB expert discussion (if a change manager can't participate, another person can note these)
| Identify training needs | Training lead | - | - | As with change impacts, ideally someone notes training needs during the 'fit-to-standard' discussion. This can include the tangible process specific points, but also other points by observing how easy it is for LoB experts to understand the vision and demo solution. (Potentially the same person can focus on capturing change impacts and training needs).
| For gaps identified, start the discussion on solutions |  |  |  | Where it makes sense start the discussion in the workshop
| Potential process adaptations to switch to SAP standard | Lead CE / LoB CE | - | - | Pros and cons, is the existing process really a USP?
| Configuration options to investigate | Lead CE / LoB CE | - | - | Check if there is anyway to close the gap with standard configuration
| Potential 'in-app' key-user developments/extensions | Lead CE / LoB CE | - | - | Examples: custom fields, layout changes, output forms/email changes, custom business objects/logic
| Potential 'in-app' developer developments/extensions | Lead CE / LoB CE | - | - | Examples: extensions of released SAP objects, custom apps
| Potential 'decoupled' side-by-side developments/extensions | Lead CE / LoB CE | - | - | Examples: custom apps (ABAP, Java, JS, Python, etc.)
| Potential CDS view or analytical query or app customisations | Lead CE / LoB CE | - | - | Examples: adding fields to CDS views, creating new views (really a subset of above categories, but worth calling out individually)
| Note potential integration requirements if any 'side-by-side' developments are envisioned | Lead CE / LoB CE | - | - | Decoupled 'side-by-side extensions identified above will require integration
Immediate follow up after 'fit-to-standard'
| Ensure all requirements and gaps are updated in Cloud ALM | Lead CE / LoB CE | ALM | -
| Discuss change management impacts with change manager | Lead CE / LoB CE | - | - | Add key topics to project change impacts log
| Loop back to confirm DDA scope | Lead CE / LoB CE | DDA | -
| Start formal tracking and reporting of gaps and developments | Lead CE / LoB CE | ALM | -
| Update resourcing requirements for developers or specialists based on gaps identified | PM / Lead CE / LoB CE | - | -
| Formal sign off on 'fit-to-standard' by LoB experts | LoB experts | - | - | Two very important formal sign offs to proceed: - 1) confirmation of standard processes 'fit' for the business - 2) clear identification of any gaps that need to be resolved.
| Special business topics for business process 'fit-to-standard' |  |  |  | Either covered in LoB fit to standard where releveant, or separate session
Responsibiity management
| Demo responsibility management | Lead CE / LoB CE | S4 SS | - | Responsibility managemnet (1NJ) in Signavio Example: defining team/persons for purchase req approval
| Identify LoB scenarios for responsibility management | Lead CE / LoB CE | - | -
Situation handling
| Demo situation handling | Lead CE / LoB CE | S4 SS | - | Situation handling (31N) in SAP Signavio Example: Expiring contracts
| Identify LoB scenarios for situation handling | Lead CE / LoB CE | - | -
Business workflows
| Demo business workflows | Lead CE / LoB CE | S4 SS | -
| Identify LoB scenarios for business workflow | Lead CE / LoB CE | - | - | Many function specific apps exist to define workflows
Intelligent Scenarios
| Demo LoB relevant signavio intelligent scenarios | Lead CE / LoB CE | Signavio/S4 SS | -
| Identify any LoB scenarios for implementation | Lead CE / LoB CE | Signavio/S4 SS | -
| Demo of SAP Build Process Automation | Lead CE / LoB CE | S4 SS | - | If more advanced workflow/automation needed (Requires additional license)
| Detailed list of embedded analytics topics |  |  |  | Either in business process 'fit-to-standard' or separate sessions
| Demo LoB relevant CDS views and analytical queries | Lead CE / LoB CE | S4 SS | - | - View browser for CDS views - Query browser for analytical queries
| Demo LoB relevant embedded anlaytics capabilities | Lead CE / LoB CE | S4 SS | -
| Analytical list reports | Lead CE / LoB CE | S4 SS | - | These contain a mix of analytic figure and transaction lists - action oriented
| Multidimensional reports | Lead CE / LoB CE | S4 SS | - | Display data about a focused topic (e.g. Sales Orders) in SAP Web Dynpro apps with a table (grid) or graphical display.
| Analytical path framework apps | Lead CE / LoB CE | S4 SS | - | These drill down to influencing data with a mix of tables and charts
| Data Analyzer | Lead CE / LoB CE | S4 SS | -
| Review booklets | Lead CE / LoB CE | S4 SS | - | - Aggregated view of business data combining: - Predefined business pages - Analytical components
| SAC stories | Lead CE / LoB CE | S4 SS | - | - Use charts, graphs, text, images, and other elements to visualize data - Predefined embedded stories included in license
| KPIs and KPI tiles | Lead CE / LoB CE | S4 SS | - | - KPIs can link to generic drill downs or analytical path framework drilldowns
| Launchpad app design for embedded analytics | Lead CE / LoB CE | S4 SS | - | - KPI tiles as well as any analytic app can be added to launchpad for frequent access, decide which to include, where for each role
| Identify any requirements not met by standard views/queries/reports | Lead CE / LoB CE | - | - | For example: - Additional fields - Combining data from two existing CDS views, etc.
Assess integration
| Review list of applications that will send or receive data to S/4HANA | Lead CE/LoB CE | DDA | -
| Update integrations in Cloud ALM by business process | Lead CE/LoB CE | ALM | Requirements
| Gather detailed requirements for integrations | Lead CE/LoB CE | ALM | Requirements | Consider SAP Integration Solution Advisory Method (ISA-M) May require a workshop or series of workshops by integration
Assess data migration
| Identify extract process for each in-scope data object | Lead CE/LoB CE | - | -
| Confirm data is ready for extract from legacy system | Lead CE/LoB CE | - | - | All cleansing/fixing in legacy system is completed
| Initial extract of master data from legacy system for migration | Lead CE/LoB CE | - | - | This data once cleansed will be loaded to S/4HANA
| After initial extract control data creation or change process in legacy system | Lead CE/LoB CE | - | - | Try to avoid creation of additional data requiring cleansing, two appraoches: - Plan a delta extra later for new data or changed data - Capture new data or changed data in parallel in project documents
| Cleansing of master data extracts in it's current format/structure | Lead CE/LoB CE | - | - | De-duplicate, remove unused data, correct missing/incorrect data
| Initial extract of transactional data for analysis of balances and open items analysis (not for migration at this point) | Lead CE/LoB CE | - | - | Review all balances for accuracy. Review all open items especially old items that may need to be cleared
| Assess migration options | Lead CE / LoB CE | S4 | Migration cockpit | The migration cockpit includes detailed instructions and upload templates for a wide range of objects. There is also a direct transfer option for SAP source systems.
| Where migration cockpit will be used, download the migration object template and review instructions and data structure | Lead CE/LoB CE | S4 | Migration cockpit | Templates can be downloaded in XML. They include detailed instructions and field by field descriptions of the S/4HANA format
| Identify gaps between legacy system data structure/format etc. and S/4HANA structure/format | Lead CE/LoB CE | - | Migration templates | Identify where mappings and other adjustments are required
Assess testing
| The scope and gaps provide a starting point to identify test requirements. This will be a key input for test planning later. | - | - | -
| Understand test phases and options. | - | - | - | Test phases include: unit, integrated, acceptance, and regression Options include manual testing and automated testing.
Assess end user training requirements
| Consolidate training needs from 'fit-to-standard' workshops | - | - | -
| Gather additional information to idenfity training required | - | - | - | Suggest a core project team workshop and interviews/surveys to key stakeholders, experts and selected users. Training should range from conceptual topics such as 'cloud mindset' to LoB technical process training to future run and operational support model.
Assess run / operation model
| Assess current ERP management model | IT operations | - | - | Topics include: incident management, change management, problem management, service levels, availability, capacity, escalations, provisioning, etc.
| Assess best practices for ERP management | IT operations | - | -
Change and communications management
| Hold detailed change assessment workshops and surveys |  |  |  | Focussing on Prosci ADKAR: - K: knowledge on how to change - A: ability to implement required skills and behaviours
| Consolidate change impacts from 'fit-to-standard' workshops and combine with earlier change impacts analysis | Change manager | - | -
| Assess change impacts, prioritise, and identify actions | Change manager | - | - | Led by change manager, consult with experts as needed
| Project team change impacts workshops | Change manager | - | - | Everyone on the team is responsible to identify change impacts and build actions into their work to address them, so suggest a project team workshop to review gathered information and discuss actions
| Stakeholders discussion on change impacts | Change manager | - | - | The updated change impacts and their actions should be reviewed with stakeholders
| Request formal confirmation from stakeholders on 'fit-to-standard' outcome and gap sign off by appropriate LoB expert | Change manager | - | -
Project and stakeholders management
| Assess benefits vs. 'fit-to-standard' outputs | Project manager | - | - | Have workshops confirmed standard processes 'fit' and will delivery expected benefits. Identify the impact of gaps on the benefit case
| Staffing of specialists / developers based on gaps | Project manager | - | - | The nature of gaps may at this stage indicate a need for specific expertise e.g. integration / ABAP / JavaScript etc.
| Update project management based on explore (assess) | Project manager | - | - | Check/update scope, resources, budget, timeline etc.
| Critical: identify and discuss any gaps that have questionable feasibility with S/4HANA Cloud public | Lead CE / LoB CE | - | -
| Critical: identify any process areas that did not reach clarity during 'fit-to-standard' | Lead CE / LoB CE | - | - | Often a lack of clarity can hide complexities or other challenges: undocumented systems, lack of internal knowledge, etc.
| Project management publishes detailed plan for EXPLORE (DESIGN) | Project manager | - | -
EXPLORE (DESIGN)
Standard processes
| For standard processes that were accepted during 'fit-to-standard' formalise these as the future design. | Lead CE / LoB CE | - | -
Fiori design
| Decide whether SAP Mobile Start Up will be used | Lead CE / LoB CE | S4 SS | - | For mobile access to Fiori Apps Requires set up and configuration in SAP Build Work Zone (BTP)
| Launchpad design | Lead CE / LoB CE | S4 SS | -
| Design space/page structure for each role | Lead CE / LoB CE | S4 SS | - | This will need to be done in parallel with role design - Typically 1 space per business role with multiple pages - The business role drives the apps that appear and the data access.
| 'My Home' - decide whether to turn on news | Lead CE / LoB CE | S4 SS | - | SAP recommends RASD news feed as a minimum for release updates
| 'My Home' - design of 'insights' | Lead CE / LoB CE | S4 SS | - | Tiles are popoulated based on monitoring Apps in business role Users can manually add cards (analytical, list, table, etc.)
| App to page design | Lead CE / LoB CE | S4 SS | - | Confirm business roles have all expected apps (via catalog) Design layout of spaces and pages
Responsibility management / situation handling / business workflow design
| If requirements were identified in 'fit-to-standard' build designs | Lead CE / LoB CE | S4 SS | - | Design covers teams, team members, tasks, etc.
Embedded Analytics Design
| Identify embedded analytics apps for each role/user | Lead CE / LoB CE | S4 SS | -
| Gather detailed requirements for any custom development | Lead CE / LoB CE | S4 SS | - | - Custom CDS views or analytical queries - Fiori app for launchpad based on report - KPI tiles - Visualisations adjusting standard apps
Design any custom changes to embedded analytics
| Design for users and authorisation (testing & production) |  |  |  | Can start when scope is confirmed Role design and build can take weeks to months, don't leave it late
| Build a role matrix to ensure role design is comprehensive and capture complex user - role - catalog - space - page mapping | Lead CE / LoB CE | - | - | A role matrix can document key things linked together: - users, business roles, catalogs, localisations, spaces, pages
| Identiy SAP standard roles which fit requirements | Lead CE / LoB CE | - | -
| Design custom business roles for gaps | Lead CE / LoB CE | - | - | Including: - Role to catalog design (catalogs control access to data and apps) - Role to Fiori space(s) and page(s) design
| Check/validate segregation of duties requirements | Lead CE / LoB CE | - | - | SAP roles are designed with this in mind, but should be validated
| Check/validate delegation of authority requirements | Lead CE / LoB CE | - | -
| Design role localisation requirements - Localisaiton means restricting access for example by company code - Plan out detailed restrictions for ALL BUSINESS ROLES | Lead CE / LoB CE | - | - | Recommended to follow 'minimum possible access principle' - No standard roles in production - All roles should be localised (restricted)
| Business role to business catalog design | Lead CE / LoB CE | - | - | Business role contains business catalogs which grants permission for apps/data
| Business role to space design | Lead CE / LoB CE | - | - | Business role also needs an assigned launchpad space - No apps will display if there is no assigned space - For custom business roles you need to create custom spaces/pages
| Confirm business roles planned for users give all required apps | Lead CE / LoB CE | - | -
| Design integration between corporate identity management and SAP to replicate employees to SAP to become users | Lead CE / LoB CE | - | - | While users are loaded manually for demo and development, the users for test and production should come from employee systems, there are multiple options including: 1) point to point, 2) BTP master data service, 3) SOAP API
| Design for custom developments |  |  |  | For any of these specific plans are needed for each dev
| Confirm requirements are clear for each gap requiring custom dev | Lead CE/LoB CE | - | - | Requirements should be clear in terms of: process steps, data, report outputs, human interaction etc.
| Draft conceptual design | Lead CE/LoB CE | - | - | Create clear conceptual design for process, data, etc. to assist with solution consideration and selection
| Investigate solution options |  |  |  | Generally choose simplest approach
| Check if relevant apps support 'in app' key user extensibility | Lead CE/LoB CE | Fiori app library | - | Fiori App library > more documentation > app extensibility Check for business context showing custom fields and custom BAdIs
| Check 'in-app' 'runtime authoring' is an option | Lead CE/LoB CE | Fiori apps | - | Adapting UI directly in Fiori apps. Examples: move fields, add existing fields from business context etc.
| Check 'in-app' developer extensibility options | Lead CE/LoB CE | S4 CAP | - | Developing in Cloud ABAP environment Only for released objects and predefined extension points
| Check 'side-by-side' low/no code extensibility options | Lead CE/LoB CE | BTP Build | -
| Check 'side-by-side' code extensibility options | Lead CE/LoB CE | BTP BAS | -
Document design for chosen approach
| Design 'In-App' key user developments | Specialist | - | -
| Design 'In-App' developer developments | Developer | - | -
| Design 'side by side' low/no code developments | Specialist | - | -
| Design 'side by side' code developments | Developer | - | -
| Update ALM | Lead CE / LoB CE | - | - | Up date as and when each gap/development changes status
| Update business roles design for custom developments | Lead CE / LoB CE | - | -
| Side-by-side solutions require integration: check prepackaged integration to support side by side build | Developer |  | Business accelerator
Design for integration
| Conceptual design for each required integration |  |  |  | Ensure system details, data, and security are clear
| Mapping of IT integration strategy with SAP recommended tools |  |  |  | To avoid proliferation of integration technologies, ensure strategy and principles are clear before going into specific solutions
Consider SAP integration options where relevant
| Start by searching SAP best practice integrations in Signavio | LoB CE | S4 | Signavio | Prepackaged integrations. Documented in Signavio (SAP manages these and maintains through releases)
| Download set up guide and review pre-requisites and suitability | LoB CE | S4 | Signavio
Set up integration
| Customer-driven integrations using public APIs from accelerator hub or custom developed | Integration lead | Web | Business accelerator | Library of predelivered public APIs SAP/partner managed APIs/integrations/other extensions (Internally managed)
| Build design for each system that sends/receives to/from S/4HANA | Integration lead | - | -
| Update business roles design for integration | Integration lead | - | -
Data migration
| Conceptual design for mappings | Lead / LoB CE | - | - | If legacy system data structures are very different from SAP, and/or SAP is an opportunity to create a new harmonised data model, this mapping may be complex and may require significant thought, and careful alignment and approval
Design for cutover
| Initial high level plan for cutover | Project manager | - | - | Timing, roles, activities, etc.
Organisation design impacts
| The change in processes and roles may require some adjustment to organisation structure. This should be investigated and designed | Project manager | - | -
| Decide if key user/super user/business support specialist concept is relevant. If so design role and identify users. | Project manager | - | -
Design for run/operate
| Map 'as is' to 'best practices', include: | IT contact | - | - | It's likely many process will change to standard software as a service platform/software as a service processes with SAP
| Incident, change, problem management | IT contact | - | -
| Service levels | IT contact | - | -
| Escalations | IT contact | - | -
| Production operation team structure | IT contact | - | -
| Business continuity plans and disaster recovery approach | IT contact | - | -
| Ongoing release udpate strategy | IT contact | - | - | Need to consider standard processes and any custom developments
| Post produciton approach to projects, developments, etc. | IT contact | - | - | This topic should include new 'parallel line' versioning approach
| Identify change impacts for change to run/operate approach and update change impacts and actions plan | Change manager | - | -
Preparation for testing (design approach)
| Design approach for tests | Project manager or test manager | - | - | Manual tests vs. automated tests Including unit, integrated, acceptance, and regression tests Testing of business processes, data migration, integrations, roles Development system vs. test system testing Approach to document testing and sign off (including Cloud ALM)
End user training
| Create detailed training plan | Project manager | - | - | This should be very detailed, include topics, audiencies, methods, timing, qualification approach, etc.
| Scope of training: general topics + LoB topics | Lead CE / Lob CE
| Audiencies: LoB experts, key users, end users, stakeholders |  |  |  | Consider training needs for different audiences
| Training method | Lead CE / Lob CE | - | - | Online/self service, classroom, webinar
| Training materials |  |  |  | SAP standard, custom, third party
| Training timeline | Lead CE / Lob CE | - | - | Training of accepted standardised processes can start as soon as they are confirmed following 'fit-to-standard' Training for custom processes have to wait until design is complete.
| Define training approach for post-go live | Lead CE / Lob CE | - | - | Training for new employees after the project.
Change and communications management
| Design materials required for change impacts and actions | Change manager | - | -
| Communication materials | Change manager | - | -
| Confirm with stakeholders the scope of processes confirmed as standard | Change manager | - | -
| Inform stakeholders about gaps identified and potential solutions | Change manager | - | -
Project and stakeholder management
| Review gaps and selected designs | Project manager | - | - | Confirm all gaps have a feasible design option selected for build
| Assess design impacts on benefits | Project manager | - | - | Update the benefit tracker based on design options
| Staffing of specialists / developers based on design options selected | Project manager | - | -
| Update project management based on selected design | Project manager | - | - | Costs, risks, timeline, etc. as needed
| Project management publishes detailed plan for next phase | Project manager | - | -
| Project management publishes high level plan for phase after next phase | Project manager | - | -
REALISE - BUILD
| Phase kick off | Project manager | - | -
Provision S/4HANA development system
| Provision S/4HANA development system | IT contact | SAP for Me | - | S/4HANA development S/4HANA customising
Prepare CBC for S/4HANA development system
| Create two workspaces in CBC | Lead CE | CBC | - | S/4HANA development system client 80 (development) S/4HANA development system client 100 (customising)
| Add team members to workspaces | Lead CE | CBC | - | Initially: Partner LoB CEs, IT contact, customer and partner project managers
| Set deployment targets | Lead CE | CBC | - | Assign the workspaces to the target development system clients
| Finalise scope and transfer to ALM and CBC: |  |  |  | So far the scope is formally documented in the DDA. This is first transferred to Cloud ALM which is used to manage the implementation. It can be reviewed and formall signed off there. Next it's transferred to CBC to start the build activities.
| Confirm DDA has 'fit-to-standard' and other updates | IT contact | DDA | -
| Transfer scope from DDA to ALM: | IT contact | DDA to ALM | -
| Extract scope from DDA to JSON file | IT contact | DDA | Supply chain of selling | DDA > supply chain of selling app > customer assessment > import & expert > export to JSON
| Import scope from JSON to project management environment | Lead CE | ALM | Scope app
| Review and validate scope in project management environment: | Lead CE | ALM | Scope app
| Collaborative review with business, IT, and project managers | Lead CE | ALM | Scope app | Ensure all knowledgable parties review scope
| Adjustment scope if needed | Lead CE | ALM | Scope app
| Validate and formally sign off scope | Lead CE | ALM | Scope app | Record formal sign off that all processes are captured in Cloud ALM
| Transfer scope from project management to configuration environment: | Lead CE | ALM | -
| Extract scope from Cloud ALM to JSON file | Lead CE | ALM
| Import JSON scope file to Central Business Configuration | Lead CE | CBC | - | workspace > define scope > click open > select 'import scope from JSON file > view details, check warnings etc, then import
Configure scope, ledgers, and primary finance settings
| Check/adjust scope bundle selected from upload. Review the processes included in the scope bundle. | Lead CE | CBC | - | Scope & Organisational Structure > Define Scope > Open: 1) Baseline Accelerator: minimum scenarios (mainly finance) 2) Enterprise Management: for large enterprises. 3) Retail bundle: contains scenarios relevant for the retail industry. 4) Public Sector Management
| Check/adjust additional processes selected from upload. | Lead CE | CBC | - | To display non-standard/license-dependent items set locked/unlocked filter to all Watchout for caution icon: marks important requirements/implications
| Check/add additional countries and regions if required | Lead CE | CBC | -
| Check/add additional languages if required | Lead CE | CBC | -
| Check/add parallel valuation if required | Lead CE | CBC | - | 0L is default ledger. 2L can be added for IFRS, 3L for US GAAP, 4G for group valuation. Important: cannot be modified later
| When scope selection is complete, confirm it | Lead CE | CBC | -
| Loop back and update Cloud ALM with any changes made in above steps | Lead CE | CBC | - | Keep Cloud ALM in sync with CBC
Primary finance settings
| Choose financial statement version (FSV) | Lead CE | CBC |  | One FSV applies to entire system (all ledgers and company codes)
| Choose group currency | Lead CE | CBC |  | The global currency applies to entire system
Organisation structure
| Set up local entities, for example: | Lead CE | CBC | Organisation structure | Entities required are based on activated scope, country/regions
| Company and company codes | Lead CE | CBC
| Sales organisations | Lead CE | CBC
| Plants | Lead CE | CBC
| Set up global entities, for example: | Lead CE | CBC
| Distribution channel, division, purchase organisation, sales office, shipping point, etc. | Lead CE | CBC
| Confirm the organisation entity set up is complete | Lead CE | CBC
| CBC direct deployment |  |  |  | Scope, ledgers, organisation structure, primary finance settings
| Deploy CBC defined configuration to S/4HANA development | Lead CE | S/4 D-C |  | Scope and organisation > organisational structure > deploy (may take hours, check in 'deployment target app'
| Verify deployment successful and system accessible | Lead CE |  |  | Verify before moving on to LoB configuration
| Release change requests (transports) for CBC defined configuration in S/4HANA development | Lead CE | S/4 D-C | Export customising transport | CBC deploys the global settings to S/4HANA development, but we still need to release the transorts for the later move to testing/production
| Set project team users up in S/4HANA development: |  |  |  | In development standard roles can be used for general configuration and testing
| Create users for project team in S/4HANA dev |  | S/4 D-C | Manage workforce app | CSV upload
| Assign project roles for development/customisation |  | S/4 D-C | Maintain business roles Maintain business users
| LoB configuration |  |  |  | CBC acts as a hub here, you link into S/4HANA dev
| Identify and work through required configuration points in CBC | LoB CE | CBC | - | Map BDCQ on: BDCQ topic = CBC title, BDCQ SAP ID = CBC ID Use filter bar and search box based on scope
| Complete necessary configurations & add to change requests. Each configuration point in CBC will include a link to a Fiori app to complete the configuration in S/4HANA development system. | LoB CE | CBC | - | Link in title field in CBC launches configuration activities, enter values Use fit-to-standard notes, BDCQ, and Cloud ALM Majority of configuration activities are same/similar to S/4HANA private/on-premise
| Double check all go-live reference 'mandatory' and 'recommended' items have been reviewed and configured | LoB CE | CBC | - | These are where SAP suggests standard values should be validated/changed
| Validate configuration works as expected | LoB CE | CBC | -
| Update CBC configuration item status from open to complete when changed | LoB CE | - | - | Change configuration status in CBC from open to complete
| Current settings in development system customising client |  | - | -
| Complete configuration settings which cannot be transported in S/4HANA development | LoB CE | S/4 D-C | Implementation activities | See list of 'current settings', for example: maintain profit center hierarchy
Build custom roles:
| Create localised roles (restricted) | LoB CE | - | Maintain business roles | Two ways to restrict role access: - Add/remove catalogs from a role - Add restrictions within a business role
| Build custom business roles | LoB CE | - | Maintain business roles | Create custom roles and assign business catalogs to them
| Assign custom business roles to Fiori space(s) and page(s) | LoB CE | - |  | Assign role to space(s) and pages to space(s)
| Create test users in dev system to test custom roles | LoB CE | S/4 D-C | Manage workforce app | CSV upload
| Assign custom roles to test users | LoB CE | S/4 D-C | Maintain business roles Maintain business users
| Assign launchpad space to users | LoB CE | -
| Add business role configuration to transport requests | LoB CE | -
Start moving from gaps to developments
| Analyse 'fit-to-standard' gaps and confirm which require custom development | - | - | -
| Track custom development in project management | Lead CE / LoB CE | ALM | -
| Prepare options analysis for each gap/development | Lead CE / LoB CE | ALM |  | Options should consider: different technical approaches, feasibility, impact analysis, effort analysis, future proofing
| Select and approve development approach | LoB expert | ALM | -
| Update mapping of gaps to soluton approach | Lead CE / LoB CE | ALM | - | Solution approaches are: 1) 'In-app' key user, or 'In-app' developer 2) 'Side-by-side' low/no code or 'side-by-side' code-based
| Build 'In-App' key user developments (extensions) |  |  |  | Extending released SAP objects
| Build 'In-App' key user developments, including for example: | Specialist | S4 D-C |  | Adjust plan based on in-scope developments
| Custom fields/ UI layout | Specialist | S4 D-C | Custom fields app
| Forms and templates - create custom templates | Specialist | S4 D-C | Output Parameter Determination | Form templates define the layouts for PDFs for printing/email etc. Adjust channels, recipients, and templates
| Maintain email templates | Specialist | S4 D-C | Maintain email templates | Copy and change standard templates and assign to business processes
| Business objects and business logic | Specialist | S4 D-C | Custom business objects/logic
| Build 'runtime authoring' |  | S4 D-C |  | Adjust Fiori apps within the app (option when no key user extensibility) Examples: hide fields, add field from business context, move fields around
| Create custom apps as a user-interface to another location | Specialist | S4 D-C | Custom tiles app | Create an app to link to an external app or website
Build 'In-app' developer developments (extensions)
| Build more complex extensions and apps | ABAP developer | S4 D-D | S/4HANA Cloud ABAP environment | Approach will depend on topic
Build 'Side-by-side' extensions
| Build side-by-side extensions and apps using low/no code | Specialist | BTP | Build | BTP SAP Build for low/no code: Build Apps, Build Process Automation, Build Work Zone (inlcued in Grow with SAP)
| Build side-by-side extensions and apps using code | Developer | BTP | Business Application Studio | BTP SAP Business Application Studio for Java, JS, Python, etc. development with Cloud Application Programming Model
| Build integration required for any side-by-side extensions | Developer | BTP |  | Depends on integration approach
| Unit test development in S/4HANA development | Lead CE/ LoB CE | - | -
| Create compliance plan for custom developments | Lead CE/ LoB CE | - | - | Data extensions are outside of SAP delivered compliance e.g. data protection
| Create operations plan for custom developments | Lead CE/ LoB CE | - | - | Management approach including release upgrade testing etc.
Prepare country localisation in CBC (if in scope)
| Set up countries not covered by best practices if required | Lead CE | CBC | Configuration localisation tool | Copy SAP delivered local country to customer localisation country. If a country not covered by best practices is required, start by copying business processes from a country with best practices to the target country.
| Identify SAP delivered local versions required | Lead CE | Signavio | - | Note public cloud covers 60 standard local versions, 31 languages
| Activate SAP local versions in CBC | Lead CE | CBC | - | Also update Cloud ALM
| Identify customer local versions required | Lead CE |  | - | Identify any countries required not covered by SAP
| Create customer local version (start from copy of SAP country | Lead CE | CBC | configuration localisation tool
| Create organisation structure for customer local version | Lead CE | CBC | -
| Deploy localisations to S/4 HANA dev | Lead CE | CBC | -
Fiori Build
| Create custom space and page(s) for custom business roles | Lead CE / LoB CE | S4 D-C | - | Each standard role has a standard space template
| Configure SAP mobile start app | Lead CE | BTP | SAP Build Work Zone | Customer IT contact provides permissions for Build Work Zone (it's on BTP)
| Customise Fiori access if required | Lead CE / LoB CE | S4 D-C | Maintain Business Roles | Two methods: - Add/remove catalogs from business roles - Add restrictions to business roles
Build for special topics (if in scope)
| Responsibility management |  |  |  | Responsibility managemnet (1NJ) in Signavio For example define approval flow for purchase req.
| Create and manage teams | LoB CE | S4 D-C | Manage teams and responsibilities
| Create and manage responsibility definitions | LoB CE | S4 D-C
| Create and manage team member functions | LoB CE | S4 D-C | Process specific workflow apps
| Add workflow, define preconditions | LoB CE | S4 D-C | Process specific workflow apps
| Situation handling |  |  |  | Situation handling (31N) in SAP Signavio Automatically inform users about situations requiring attention
| Identify which situation handling templates are relevant (per LoB) | LoB CE | S4 D-C | -
| Identify which are enabled by default, and which not | LoB CE | S4 D-C | -
| Decide if any not enabled by default should be enabled | LoB CE | S4 D-C | -
| Gather necessary information | LoB CE | S4 D-C | -
| Building teams | LoB CE | S4 D-C | -
| Adding members | LoB CE | S4 D-C | -
| Defining tasks (member functions) | LoB CE | S4 D-C | -
Business Workflow
| Review existing workflow scenario templates | LoB CE | S4 D-C | -
| Match to requirements in fit-to-standard | LoB CE | S4 D-C | -
| Create or maintain custom approval: | LoB CE | S4 D-C | -
| Open function-specific workflow app | LoB CE | S4 D-C | -
| Adjust work items/tasks/agent assignment | LoB CE | S4 D-C | -
| Decide on whether SAP Build Process Automation Is Needed | LoB CE | S4 D-C | - | Part of Grow with SAP, runs on BTP, low/no-code workflow Combines traditional workflow and robotic process automation
Intelligent scenarios
| If an LoB has an intelligent scenario that is required, these need to be set up by LoB CE in S/4HANA development | LoB CE | S4 D-C | - | Check set-up instructions in SAP Signavio Process Navigator
Build for Embedded Analytics
| Copy and customise existing CDS views/analytical queries in S/4HANA development customising client | Lead/LoB CE | S4 D-C | Custom CDS views Custom analytical queries | Copy from standard and adjust, or create from scratch Example: create a custom analytical query from a CDS view
| Create custom KPIs, reports, SAC stories if required | Lead/LoB CE | S4 D-C | Manage KPIs and reports app
| Create custom launchpad apps for embedded analytics apps | Lead/LoB CE | S4 D-C | Manage KPIs and reports app | Assign app to custom business catalog, assign catalog to business role Add app to launchpad page (mapped to the business role)
Build for integrations
For SAP best practices integrations - typical steps:
| Prerequisites: access to systems | LoB CE | -
| Prerequisites: authorisations | LoB CE | -
| Set up communication users | LoB CE | S4 D-C | Maintain communication user | For authentication when sending/receiving messages
| Set up communication user authentication | LoB CE | S4 D-C | - | Password or certificate/token based
| Create communication system | LoB CE | S4 D-C | Maintain communication system | Inbound or outbound
| Create communication arrangement | LoB CE | S4 D-C | -
For customer-driven integrations
| Follow guides based on selected approach | LoB CE/specialist |  |  | Set up is specific to the API chosen
| Familiarise and set up monitoring in Cloud ALM | LoB CE | ALM | Various | Landscape management and external API management apps. Capabilities include: Business Process Monitoring, Integration & Exception Monitoring, User & Performance Monitoring, Job & Automation Monitoring, Configuration & Security Analysis, Health Monitoring, Business Service Management, Intelligent Event Processing
Build for data migrations
| Use conceptual mapping design to update mapping in S/4HANA | LoB CE | S4 D-C | Migration cockpit | Mapping can be entered directly in Migration Cockpit, or an excel template can be downloaded, filled in, then uploaded
Testing
| Regression testing for release upgrades during implementation |  |  |  | Release upgrades will be applied during project (at least one)
| Set up test process automates in test tool in parallel with configuration | Lead CE/LoB CE | - | -
| During release upgrade pause work and re-test already validated items | Lead CE/LoB CE | - | - | Check release upgrade did not impact any already unit tested items
Unit testing in development
| Create unit test list | Lead CE/LoB CE | - | - | Easily created based on scope + configuration points + custom developments
| Execute unit tests in development system where possible | Lead CE/LoB CE | - | - | Where sufficient data exists unit test in development
| Change request 'transports' management |  |  |  | The CR/transport system will be used to move from dev to test
| Check/validate all CBC direct configurations CRs are tracked | PM | S4 D-C | - | CBC deployed these to dev, but they will move to test with CRs
| Check/validate all LoB configuration CRs are tracked | PM | S4 D-C | - | These are managed with CRs
| Check/validate all custom development CRs are tracked | PM | S4 D-C | - | These are managed with CRs
Training delivery
| In parallel with build training delivery can start on concepts and standard processes etc. | Training lead | - | -
Change and communications management
| Regular updates with stakeholders on change impacts | Change manager | - | -
| Update stakeholders on progress of build of developments selected | Change manager | - | -
| Update stakeholders on training results | Change manager | - | -
Project and stakeholder management
| Check benefits vs. devleopment build | Project manager | - | -
| Stakeholder updates during build | Project manager | - | - | Topics to cover: - Progress on change impacts (comms, training, developments)
| GO / NO GO for REALISE (BUILD TEST SYSTEM) | Project manager | - | - | Check: - Core build (standard processes) - Custom roles - Custom developments
| PM publishes high level plan REALISE (BUILD TEST SYSTEM) | Project manager | - | -
REALIS - BUILD TEST SYSTEM
| Phase kick off | Project manager | - | -
Provision and configure S/4HANA test system for testing
| Provision S/4HANA test system | IT Contact | SAP for Me
| Build test system - move change requests/transports from development to test systems | IT Contact | S4 D | - | Transports for basic configuration, roles, developments etc. all need to be moved to the test system and checked. This may be a big effort with a lot of transports. Use 'execute' option in 'release' drop down menu Note: transport has to be assigned to you to transfer
| Validate test system configuration | Lead CE LoB CE | S4 T | - | It's common to encounter problem in UAT due to missing or forgotten transports, so this should be carefully checked
| Configure current settings, for example: |  |  | - | Current settings are settings which cannot be transported, these are therefore manually done in the test system. Several examples are listed. These also need to be manually set up in production later.
| Maintain Default Profit Center | Lead CE LoB CE | S4 T | -
| Maintain Profit Center Standard Hierarchy | Lead CE LoB CE | S4 T | -
| Create Bank Master Data for House Banks | Lead CE LoB CE | S4 T | -
| Define House Banks | Lead CE LoB CE | S4 T | -
| Create Bank Accounts in Cash Management | Lead CE LoB CE | S4 T | -
| Maintain Check Lots | Lead CE LoB CE | S4 T | -
| Maintain Business Partner Representing Supplier Company Code for Intercompany | Lead CE LoB CE | S4 T | -
| Maintain Consolidation FS Items | Lead CE LoB CE | S4 T | -
| Maintain Stock Transfer Supplier BP | Lead CE LoB CE | S4 T | -
| Maintain PSM Master Data for Material Stock Postings | Lead CE LoB CE | S4 T | -
| Maintain PSM Sponsored Class Master Data for G/L Account Classification | Lead CE LoB CE | S4 T | -
| User accounts, roles, and authorisations in S/4HANA test system | Lead CE LoB CE | S4 T | -
| Business roles and authorisation build in S/4HANA test system |  |  |  | Test system approach: No standard roles, test real roles
| Confirm role matrix complete and signed off | Project manager |  |  | As a basis for successful testing ensure that the users set up match real roles and these have the correct restricted access to apps and data as they will need in production.
| Confirm custom role developments and localisation complete | Lead CE / LoB CE
| No standard roles in test/prod: Create custom roles & localise |  |  |  | No standard 'wide' access, all access to be minimised Tip: this can take weeks - months depending on project size
| Create business roles | Lead CE / LoB CE | S4 D | Maintain business roles | Suggest to build in restrictions to naming - Example: add company code, plant, etc. to role name
| Adjust access categories for roles | Lead CE / LoB CE | S4 D | Maintain business roles | SAP recommends all roles are set to 'restricted' and apply restrictions
| Assign business catalog to roles | Lead CE / LoB CE | S4 D | Maintain business roles | Business catalogs control access to apps and data
| View and maintain restrictions | Lead CE / LoB CE | S4 D | Maintain business roles | Define restrictions for every field e.g. select company codes
| For all roles check/adjust assigned launchpad space(s) | Lead CE / LoB CE | S4 D | Maintain business roles
| For all launchpad space(s) check/adjust assigned page(s) | Lead CE / LoB CE | S4 D | Maintain launchpad spaces | Edit pages to add/remove apps and change how they are displayed
| Transport business role configuration to test system | Lead CE | S4 D | -
| Create users in S/4HANA test system | Lead CE | S4 T | -
| Connect IAS to corporate identity provider (IdP) | Developer | IAS / IdP | - | The set up of this may require a stand alone project. The idea is to base the users in S/4HANA test and production on the actual employees from the employee identity management system.
| Replicate users to IAS using selected integration solution | IT Contact | IAS / IdP | - | Options: point to point/BTP master data service/SOAP
| Assign business roles to users | Lead CE | S4 T | Maintain business roles Maintain business users
| Assign launchpad space to users | Lead CE | S4 T | -
| Activate users | Lead CE | IAS | - | Download from S/4HANA testing and upload to IAS to send activation
Data migration to test system for testing
| Define scope of data migration for testing | Project manager | - | - | Classicaly only a subset of data is used for user acceptance testing. At minimum a variety of data to test all processes. Full data migration can be tested in a trial cutover test. However, if a trial cutover test is not planned, it may be sensible to load all data for UAT
| Finalise/update templates and mappings from design phase | Lead CE / LoB CE | - | -
| Execute main master data migration | Lead CE / LoB CE | - | - | (limited or full scope depending on strategy)
| Execute any delta master data migration | Lead CE / LoB CE | - | - | (only if aiming for full scope)
| Reconcile master data migration | Lead CE / LoB CE | - | - | Reconcile that intended master data was correctly loaded
| Balances and transactions migration | Lead CE / LoB CE | - | - | If no trial cutover planned it may be worthwhile to test balance and transaction migration as part of UAT, but this should not hold up UAT testing (it can be loaded in a different period).
| Balance sheet: transfer opening balances | Lead CE / LoB CE | - | -
| Balance sheet: transfer open items | Lead CE / LoB CE | - | -
| Transfer P&L account line items or balances (for mid-year cutovers) | Lead CE / LoB CE | - | -
| Reconcile financial balances and transactions | Lead CE / LoB CE | - | - | Requires 100% reconciliation and no errors before production migration
Change and communications management
| Continue to capture change impacts as they emerge | Change manager | - | -
| Implement change actions based on change impact assessments | Change manager | - | - | Actions are highly specific to change impacts
| Liase with configuration experts and IT on build status and challenges encountered | Change manager | - | -
Project and stakeholder management
| Project management and stakeholder updates | Project manager | - | -
| GO / NO GO for REALISE (TEST) | Project manager | - | - | Check: - Test system ready for UAT
| PM publishes detailed plan for next phase | Project manager | - | -
REALISE - TESTING IN S/4HANA TEST SYSTEM
| Training/onboarding for test automation tool | Project manager |  |  | Used primarily for acceptance tests and regression tests
Prepare automated tests
| Choose / set up automated tests for standard processes | LoB CE/Lead CE | - | Manage Your Test Processes | Detailed steps on SAP Help
| Choose / set up automated tests for custom processes | LoB CE/Lead CE | - | Manage Your Test Processes | Detailed steps on SAP Help
| Choose / set up automated tests for post ugprade tests | LoB CE/Lead CE | - | Manage Your Test Processes | Detailed steps on SAP Help
| Run automated tests | LoB CE/Lead CE | - | Manage Your Tests
| Review automated tests results | LoB CE/Lead CE | - | Analyse automated test results
Prepare unit and integrated tests
| Define approach for unit tests and integrated tests in test systems | Project manager | - | - | SAP documentation does not treat these too formally, however in my experience if team members miss unit or integrated tests it can lead to a lot of issues in acceptance testing, so recommended formal identification and tracking of these.
| Prepare list of unit tests for test systems | LoB CE/Lead CE | - | - | Ideally majority of unit tests are done in development - customising, however some unit tests may require higher quality or more extensive data only available in test systems
| Prepare list of integration tests (SAP refers to them as string tests) | LoB CE/Lead CE | - | - | Integration tests are where several steps/tasks are tested in a chain to test integration across processes Example: chain from purchase requisition through to payment
| Formal confirmation that unit and integrated tests pass | LoB CE/Lead CE | - | - | Ensure project team members formally sign off and commit to all their unit and integrated tests being completed. This is critical to ensure a smooth acceptance test.
| Create LoB experts in Cloud ALM | LoB CE/Lead CE | Cloud ALM | - | For test tracking
Prepare user acceptance tests
| Create test cases | LoB CE | Cloud ALM | Cloud ALM test managemnet | Ensure test cases cover business roles: test authorisation, localisation, segregation of duties, delegation of authority etc. Ensure test cases cover custom developments
| Assign test cases to test plans | LoB CE | Cloud ALM
| Assign test plans to testers | LoB CE | Cloud ALM
| Invite LoB experts to UAT (share timing, meetings etc.) | LoB CE
| Run training for testers (LoB experts & others nominated) |  |  |  | Potentially key users/super users if relevant too
| Online training | Lead CE / LoB CE | - | -
| Classroom training | Lead CE / LoB CE | - | -
| Test / qualify LoB experts as ready for UAT | Lead CE / LoB CE | - | - | Online and classroom trainings can include assessment to test knowledge levels
Run testing
| Unit and integrated tests |  |  |  | Tests by LoB CE to ensure system works as designed
| Execute remaining unit tests which required S/4HANA test environment | Lead CE / LoB CE | - | -
Execute integration (string tests in SAP terms)
| User acceptance tests | Lead CE / LoB CE | - | -
| LoB expert carries out testing | LoB Expert | S4 Test
| Customer LoB document formal sign-off on test cases. | LoB Expert | Cloud ALM
| Document any role issues and resolutions for production deployment | LoB Expert | -
Change and communications management
| Continue to capture change impacts as they emerge | Change manager | - | -
| Implement change actions based on change impact assessments | Change manager | - | - | Actions are highly specific to change impacts
| Survey for feedback on testing, and identify readiness issues | Change manager | - | - | Recommend change manager to sit in on some test sessions to gauge various factors: knowledge levels, comfort levels, etc.
Project and stakeholder management
| PM publishes detailed plan for next phase | Project manager | - | -
| Phase specific project management and stakeholder updates | Project manager | - | -
REALISE - CUTOVER TEST
| Plan trial cutover |  |  |  | I haven't seen trial cutover explicitly planned in SAPs methodology, this may be a reflection of the capabilities of the migration cockpit. However, for projects with large data migrations, it may still be worthwhile planning this phase. Suggest to consult with SAP.
| Create ordered plan of cutover steps with owners | Project manager | - | -
| Identify reconciliation steps, reports, and owners | Lead CE / LoB CE | - | -
| Identify rollback appraoch in case of errors | Lead CE / LoB CE | - | -
| Identify cutover system approach | Lead CE / LoB CE | - | - | Consult with SAP, potentially: - Refresh test system from UAT - Request sandbox system - Either may involve additional costs
Execute trial cutover
| Load full volume of master data | Lead CE / LoB CE | - | -
| Reconcile master data | Lead CE / LoB CE | - | -
| Load balances for all relevant accounts | Lead CE / LoB CE | - | -
| Reconcile balances | Lead CE / LoB CE | - | -
| Load open items for open item managed accounts | Lead CE / LoB CE | - | -
| Reconcile open items | Lead CE / LoB CE | - | -
| Load P&L balance/line items in the case of mid-fiscal cutover | Lead CE / LoB CE | - | -
| Reconcile P&L | Lead CE / LoB CE | - | -
| Overall reconcilaition - compare trial balance from S/4HANA to legacy ERP | Lead CE / LoB CE | - | -
Project and stakeholder management
| GO / NO GO for production cutover | Project manager | - | - | Check: - status of trial cutover
REALISE (PRODUCTION)
Prepare for production start up
| Create production cutover plan | Project manager | - | - | If a trial cutover was held, use this plan as a baseline and adjust based on lessons learned
Provision and configure S/4HANA production system
| Provision S/4HANA production system | IT Contact | S4 P | -
| Move change request transports from S4/HANA development to S/4HANA production | Lead CE | S4 D to S4 P | - | Ensure transport list is adjusted to resolve any issues encountered during the test system set up.
| Configure current settings in S/4HANA production | Lead CE / LoB CE | S4 P | - | See example list from test phase
| Roles and authorisation design for S/4HANA production system |  |  |  | Production system approach: No standard roles, test real roles
| Follow the same steps as for the test system | Lead CE / LoB CE | S4 P | -
Support model
| Design stabilisation period support model | Project manager | - | - | Recommendations: - Use business as usual incident reporting/tracking from day 1 - Project team supplements support team during 1st month
| Plan activities and timing to handover from stabilisation support to business as usual support | Projecdt manager / IT managers | - | -
| Implement staffing/role changes in operations team if required | Team managers
| Training for operation teams and managers (end users + more) |  |  |  | Broad audience of all end users and other relevant parties If relevant identify/add key users/super users in delivery
| Publish online training | Lead CE / LoB CE | - | -
| Deliver classroom training | Lead CE / LoB CE | - | -
| Include tests to qualify individuals as ready for production | Lead CE / LoB CE | - | -
| Go/no go for data migration | Project manager | - | -
| Data migration |  |  |  | Production system approach: No standard roles, test real roles
| Finalise/update templates and mappings from test phase | Lead CE / LoB CE | - | -
| Execute main master data migration | Lead CE / LoB CE | S4 P | -
| Execute delta master data migration | Lead CE / LoB CE | S4 P | - | Delta covers data from initial extract to cutover date
| Reconcile master data migration | Lead CE / LoB CE | S4 P | - | Requires 100% reconciliation and no errors before production migration
| Open posting periods for balances and transactions migration | Lead CE / LoB CE | S4 P | - | Usually a special period
| Balances and transactions migration | Lead CE / LoB CE | S4 P | -
| Balance sheet: transfer opening balances | Lead CE / LoB CE | S4 P | -
| Balance sheet: transfer open items | Lead CE / LoB CE | S4 P | -
| Transfer P&L account line items or balances (for mid-year cutovers) | Lead CE / LoB CE | S4 P | - | Depends on cutover timing
| Reconcile financial balances and transactions | Finance | S4 P | - | Requires 100% reconciliation and no errors before production migration
| Formal finance sign off that accounts align across systems | Finance | S4 P
| Close posting periods for migrated balances and transactions | Lead CE / LoB CE | S4 P | - | These should never be modified after reconciliation
| Go/no go for production postings | Project manager | - | -
Production start up
| Post trial transctions | Operation teams | S4 P | - | Post first transactions for key processes with project team present and monitoring
| Incident management starts | Support teams | - | - | Suggest to use business as usual process, tools, team, but have project team supplement/support them
| Project team support during stabilisation period |  | - | - | Recommended until after 1 month end is complete
| Incidents related to project work assigned to project team and tracked / closed before closeout | Various | - | -
| Change requests relaed to features not in scope go into business as usual change management process | Various | - | -
| Ramp up to full transcaction volume posting / normal operations | Operation teams | S4 P | -
| Daily reporting of production start up process | Project manager | - | - | Include: posting metrics, issues, change requests
| Month end closing and reporting | Finance | S4 P | -
| Closeout of all open issues | Project team | - | -
Close out
| Review of project outcomes vs. acceptance criteria / expected benefits | Project manager | - | -
| Project closeout meeting | Project manager | - | -
| Handover support to business as usual operating model | Operations | - | -

## Terms
go back to implementation list
| Category | Term | Meaning | Details
| Roles | Lead CE | Line of business configuraiton expert | Partner / SAP expert in S/4HANA public cloud design and configuraiton for cross line of business topics
| Roles | LoB CE | Line of business configuraiton expert | Partner / SAP expert in S/4HANA public cloud design and configuration for specified line of business
| Roles | LoB expert | Line of business expert | Internal exper in the specified line of business
| Roles | IT contact | IT point of contact | Main IT point of contact, mainly responsible to co-ordinate systems provisioning in this plan
| Systems | ALM | SAP Cloud Application Lifecycle Management | A system for managing implementation and ongoing operations of S/4HANA
| Systems | CBC | SAP Central Business Configuration | A system for managing the configuration of S/4HANA public cloud - Certain 'global' configurations are done in CBC and deployed to S/4HANA - Line of business configurations are ordered in CBC with links that lead to S/4HANA configuration apps
| Systems | S4 SS | S/4HANA public cloud starter system | Demo system to assist with 'fit-to-standard'. Contains two clients: - Client 100: for the majority of configuration - Client 80: for custom developments
| Systems | S4 D-C | S/4HANA public cloud development system, customising client | The development system customising client. The majority of configuration is done here.
| Systems | S4 D-D | S/4HANA public cloud development system, development client | The development system development client. This is where more complex developments are done
| Systems | S4 T | S/4HANA public cloud test system | The test sytem. Primarily for user acceptance testing. Will also be key for unit and integrated tests requiring quality data.
| Systems | S4 P | S/4HANA public cloud production system | The production system
| Systems | IAS | Cloud Identity - Identity Authentication Service | For managing identity authentication. Generates access/activation emails for various systems.
| Systems | IPS | Cloud Identity - Identity Provisioning Service | For provisioning access.
| Tools | BDCQ | Business Data Configuration Questionnairre | A questionnairre to help ensure all business information for configuration is captured
| Tools | DDA | Digital Discovery Assessment | The initial tool to identity scope and check if S/4HANA Cloud Public or Private is most suitable.